## Product Backlog
Project Name | nimapinfotech website
Client | nimapinfotech website
Created By | Abhishek Choudhary
Creation Date | 2024-07-13
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
1 | US_01 | Sign Up | A new user can create a account by adding his valid credentials such as it's email id following with its phone no and name to generate otp and set the password. For SignIn and acess The services and features | Done | In order to create an account and generate an OTP, a new user must provide acceptable credentials, such as their email address, phone number, and name. For access and sign-in The features and services
| US_02 | Forgot Password | If user has Forgotten the password The forgot password link is present .Onclick the link the user can reset by entering the registered E-mail and so he can regain access over its account | Done | If the user can't remember their password There is a link to reset your password.By clicking the link, the user can reset and recover access to their account by providing their registered email address.
| US_03 | Sign with OTP | User Can SignIn with the help of Sign with Otp method to easily access the website without/not remembering the password by adding the registered email/phone-no for otp | Done | By entering their registered email address or phone number for OTP, users can utilise the Sign with OTP method to sigin in and conveniently access the website even if they don't remember their password.
| US_04 | Login | If user is registered they can add the valid login credentials and logIn to access the platform features | Done | When a user registers, they can enter their genuine login information and log in to use the platform's services.

## Sprint Planning
Project Name | nimapinfotech website
Client | nimapinfotech website
Created By | Abhishek Choudhary
Attendees | 1899-12-31
Creation Date | 2024-07-13
Epic | User Story ID | Feature/Title | User Story | Sprint
1 | US_01 | Sign Up | A new user can create a account by adding his valid credentials such as it's email id following with its phone no and name to generate otp and set the password. For SignIn and acess The services and features | 1
| US_02 | Forgot Password | If user has Forgotten the password The forgot password link is present .Onclick the link the user can reset by entering the registered E-mail and so he can regain access over its account | 1
| US_03 | Sign with OTP | User Can SignIn with the help of Sign with Otp method to easily access the website without/not remembering the password by adding the registered email/phone-no for otp | 1
| US_04 | Login | If user is registered they can add the valid login credentials and logIn to access the platform features | 1
Story Points | Hours
1 | 1 Day
0,1, 1, 2, 3, 5, 8 | Fibinacci series

## Test scenarios
Project Name | nimapinfotech website
Module Name | LogIn Page
Requirement Number | NA
Test case Type | Functionality Testing
Reference Doccument | NA
Pre-condition | User should create account
Test Data | https://testffc.nimapinfotech.com/auth/login
Test Senario number | Description
TS_01 | To confirm the successful user registration using accurate information.
TS_02 | To confirm Confirm that the user who registered an email address receives a password reset email.
TS_03 | Check if the user is able to log in with an OTP that was delivered to their registered email address.
TS_04 | Verify successful login with correct email and password.

## Test cases
Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date
TS_01 | Sign Up | Determine whether the user is able to reach the Sign-Up page. | Proceed to the Sign-Up section. | https://testffc.nimapinfotech.com/auth/register | It should show the Sign-Up page. | The Sign-Up page is displayed. | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_02 |  | Check that the Sign-Up form has all required fields filled in. | Navigate to the Sign-Up section. Look for any fields that are required. | https://testffc.nimapinfotech.com/auth/register | All mandatory fields should be present. | All mandatory fields are present. | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_03 |  | Confirm that the user registration method went well. | Insert true information in the form. Send it in. | Name : Abhishek Choudhary Country : India Mobile-No:7039733975 Email-ID: choudharyabhishek182@gmail.com | The user should be taken to the login page after registering. | User is sucessfully registered and redirected to the login page. | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_04 |  | Check that the user cannot register using an email address that is already registered. | "Please provide an email address that you have already registered. Complete the remaining fields. Send it in." | Name : Abhishek Choudhary Country : India Mobile-No:7039733975 Email-ID: choudharyabhishek182@gmail.com | The Error message should be displayed | The Error message is not displayed | HIGH | HIGH | ABHISHEK CHOUDHARY | FAIL | 2024-07-13 | 2024-07-14
TS_05 | Forgot Password | Check that that the user is able to reach the "Forgot Password" page. | Go to the option that says "Forgot Password." | Enail ID :choudharyabhishek182@gmail.com | A success message and an email should be sent | Success message is sent | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_06 |  | When entering a registered email, confirm that the user receives an email. | Put in a valid email address. Submit the form. | Enail ID :choudharyabhishek182@gmail.com | An error message should be displayed. | Error message is displayed | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_07 | Sign Up with OTP | Make sure the user enters a registered email address and receives an OTP. | Enter a registered email and password. Request OTP. | Enail ID :choudharyabhishek182@gmail.com | It is necessary to send an OTP to the registered email. | sent to the registered email was a verification OTP. | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_08 |  | Check to see if the user has a working OTP and can log in. | Enter a valid OTP. Submit it. |  | The user should have successfully logged in. | The user has successfully signed in. | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_09 | LogIN | Make sure the user cannot use faulty login information to log in. | "Invalid password and email entered.Send in the application." | https://testffc.nimapinfotech.com/auth/login | "Password and email entered are invalid.Submit the application." | An error notice appears. | MEDIUM | MEDIUM | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14
TS_10 |  | Check to see if the user's login credentials are genuine. | Enter a working password and email address.Send in the application." | Enail ID :choudharyabhishek182@gmail.com Password:abhi@1234 | Put in your email address and a functional password.Submit the application." | The user has successfully logged in. | HIGH | HIGH | ABHISHEK CHOUDHARY | PASS | 2024-07-13 | 2024-07-14

## Test excution details
Test Case Number | ScreenShort
TC_01
TC_02
TC_03
TC_04
TC_05
TC_06
TC_07
TC_08
TC_09
TC_10

## Defects
Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to | Screen Shots
DF_01 | NmapInfotech | LOGIN PAGE | 1 | TC_04 | Any user's email address that is already registered can be used to sign up. | There is no error message when we enter up with the same email address the first time and the second time. | It allow already registered email in sign up functionality. | HIGH | HIGH | SHUBHAM PAREKH

## Story_Point_Effort_and_Reason
Project Name :- | NimapInfotech
Story Point :- | 4
Reason for story point :-
Efforts(in hours) :- | 3
Reason for Efforts :- | 1hr for writing test-case,1 hr for testing,1 hr for finding defect

## Test report
SNO | PASS | FAIL | BLOCKERS | NOT EXECUTED | TOTAL TEST CASE | PASS RATIO (%) | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | 9 | 1 | - | - | 10 | 90% | 0 | 0 | 10 | 1